## Sheet1
BURNDOWN CHART(SPRINT 1)
| Days | Goal | Done | Goal velocity | Remaining
(Kickoff, CNN design) | 1 | 1.3 | 1 | 11.7 | 7
(Model training, latency fixes) | 2 | 2.6 | 3 | 10.4 | 7
(Overfitting issues) | 3 | 3.9 | 2 | 9.1 | 6
(UI labels added) | 4 | 5.2 | 3 | 7.8 | 7
(Low-light testing) | 5 | 6.5 | 2 | 6.5 | 6
(Model retraining) | 6 | 7.8 | 1 | 5.2 | 7
(Demo ready) | 7 | 9.1 | 2 | 3.9 | 8
(Early finish) | 8 | 10.4 | 0 | 2.6 | 8
| 9 | 11.7 | 0 | 1.3 | 8
Note on J4: stakeholdermap.com: Change the timescale to suit you needs e.g. Sprint or Iteration.
Note on K4: stakeholdermap.com: Number of features or story points you plan to complete.
Note on N4: stakeholdermap.com: Number of features or story points actually remaining at the end of each day/iteration/sprint.