## SPRINT BACKLOG
SPRINT [1] BACKLOG
ID | User Story | Tasks | Owner | Status | Estimated effort | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
US001 | Real-time emotion detection | 1. Set up webcam feed | Gopa | Completed | 54 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2. Train CNN model (FER-2013) | Gopa | Completed |  | 0 | 0 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3. Integrate model with UI | Mahithi | Completed |  | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US002 | Low-latency processing | 1. Optimize face detection | Mahithi | Completed | 25 | 2 | 3 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2. Reduce frame drops | Mahithi | Completed |  | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US003 | Emotion logging | 1. Design CSV format | Gopa | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0
US004 | Simple UI | 1. Build clinician dashboard | Mahithi | Completed | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0
[5 empty] | 99 | 6 | 7 | 9 | 9 | 10 | 13 | 7 | 8 | 7 | 7 | 4 | 0 | 0 | 0 | 0

## PROJECT DETAILS
PROJECT NUMBER
PROJECT NAME
PROJECT MANAGER
DATE
VERSION

## RESOURCES
Useful resources
Burndown Chart Template
Daily Scrum Meeting Template
Deployment Plan Template
Product Backlog Template
Project Management Templates