## SPRINT BACKLOG
SPRINT [2] BACKLOG
ID | User Story | Tasks | Owner | Status | Estimated effort | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
US005 | Multi-patient tracking | 1. Enable multi-webcam input | Team | Completed | 35 | 2 | 3 | 3 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2. Sync feeds to UI | Mahithi | Completed |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0
US006 | User access control | 1. Implement role-based auth | Rishi | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0
US007 | Privacy mode | 1. Auto-delete session data | Mahithi | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 0 | 0 | 0 | 0
US008 | Mobile support | 1. Adapt UI for mobile | Team | Completed | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0
US009 | Emotion trend charts | 1. Generate weekly graphs | Gopa | Completed | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0
US010 | Backup/restore | 1. Set up cloud sync | Rishi | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 4 | 0
[5 empty] | 100 | 2 | 3 | 3 | 4 | 4 | 4 | 5 | 7 | 14 | 14 | 12 | 12 | 12 | 4 | 0

## PROJECT DETAILS
PROJECT NUMBER
PROJECT NAME
PROJECT MANAGER
DATE
VERSION

## RESOURCES
Useful resources
Burndown Chart Template
Daily Scrum Meeting Template
Deployment Plan Template
Product Backlog Template
Project Management Templates